# Agreed Capacity Term Sheet

Reserved B200 capacity - CB-2026-041

| Buyer | Northstar Models, Inc. |
| --- | --- |
| Provider | Alder Ridge Compute Campus LLC |
| Date | August 20, 2026 |
| Drafting status | Agreed commercial terms for definitive documentation |

Synthetic matter: This is a fictional benchmark document and not legal advice or an offer of real compute capacity.

| Term | Agreed position |
| --- | --- |
| Capacity | 1,024 NVIDIA B200 SXM GPUs in 128 dedicated eight-GPU HGX B200 nodes. No shared or fractional service. |
| Delivery | All 1,024 GPUs ready for acceptance by January 15, 2027. |
| Term | January 15, 2027 through July 14, 2028, with one buyer option to extend for six months on pricing to be agreed in the definitive agreement. |
| Base price | $3.10 per accepted GPU-hour, excluding taxes. Annual escalation: 2% on each anniversary of the first service date. |
| All-in cap | The base price plus permitted operating pass-throughs may not exceed $3.35 per GPU-hour, excluding taxes. |
| Power | Power is included in the base price up to $0.075/kWh. Verified cost above that threshold may pass through at cost with invoice support, 30 days' notice, and buyer audit rights, subject to the all-in cap. |
| Deposit | Three months of committed charges, held as security, creditable against final invoices, and otherwise refundable after payment of undisputed amounts. |
| Fabric | At least one 400 Gb/s fabric endpoint per GPU; topology and port map supplied before signing. |
| Storage / ingress | 6 PiB usable storage at 1.2 TB/s read and 800 GB/s write; at least 200 Gb/s external ingress. |
| Availability | 99.5% monthly cluster availability. Service credits: 12% of monthly committed charges per percentage point below the threshold, capped at 50% per month. |
| Maintenance | Planned maintenance limited to eight hours per month with at least seven days' notice. |
| Delay credits | $300,000 for each full week of delay, capped at $2.4 million; buyer may terminate after eight weeks. |
| Acceptance | 72-hour burn-in, serial and inventory attestation, and NCCL performance against a reference and threshold to be agreed before signing. |
| Substitution | Only B200 or a later-generation accelerator with equal or better specifications, and only with Northstar's prior written consent. |
| Assignment / use | Northstar may assign to an affiliate without consent and may allocate workloads to named controlled customers, while remaining liable. No unrestricted resale. |
| Force majeure | Either party may terminate after 90 consecutive days of force majeure preventing material performance. |
| Disputes | Confidential binding arbitration under AAA Commercial Rules, seated in New York, after executive escalation. |

# Conditions to definitive agreement

Capacity control: Evidence of provider authority, utility delivery, facility commissioning, hardware title, liens, and any lender or third-party consent.

Security: Current SOC 2 Type II and agreed security schedule.

Acceptance: Agreed NCCL reference configuration and passing threshold.

Credit support: Parent guarantee from Alder Ridge Compute Holdings, Inc.

# Drafting convention

The definitive agreement should preserve these terms unless a later written negotiation record expressly states otherwise. Silence in a draft does not amend this term sheet.