# Capacity Data Room Population Plan

Blue Mesa AI Campus / Northstar Models

| Opportunity | CB-2026-041 |
| --- | --- |
| Seller group | Alder Ridge Compute |
| Prepared for | Transaction team working draft |
| Phase 1 | August 17, 2026 |
| Phase 2 | August 24, 2026 |

Purpose: This is the operating plan for collecting, reviewing, staging, and releasing evidence. A listed item is not represented as available unless its status says Ready.

Immediate gating issue: The available utility evidence supports 12 MW on January 15, 2027 and another 12 MW on April 1, 2027. It does not substantiate the buyer's requested 24 MW on January 15.

# 1. Scope and control

The room will cover Alder Ridge Compute Holdings, Inc., Alder Ridge Compute LLC, Alder Ridge Compute Campus LLC, and Northline Compute Operations LLC to the extent each entity owns, controls, finances, operates, or contracts for capacity required by the transaction. The buyer request names only Alder Ridge Compute LLC; that scope is insufficient because the project SPV controls the site and utility rights, while Northline holds GPU purchase documents and operating contracts.

| Release state | Who may see it | Use |
| --- | --- | --- |
| Phase 1 / general | Approved Northstar team after NDA | Core non-sensitive evidence and reviewed redacted copies |
| Named-party | Named legal, security, or technical reviewers | Security detail, personal information, and customer-specific material |
| Clean team | Named finance and counsel clean team | Unredacted supplier pricing, utility pricing support, and financing economics |
| Hold / escalation | No external release | Privilege, unresolved third-party restriction, export controls, or conflicting disclosure instruction |

The GPU-capacity and data-center precedent indexes are structural references only. Their corporate, capacity and hardware, facility and power, network and storage, security and data, operations and SLA, commercial, finance and insurance, compliance and disputes, site, construction, cooling and water, telecommunications, environmental, and consent sections were adapted to this compute matter. Northstar's D-01 through D-24 request controls, and irrelevant precedent sections were not carried forward.

# 2. Room structure and work plan

| Item | Document / action | DDRL | Owner | Release | Status |
| --- | --- | --- | --- | --- | --- |
| 1.01 | Entity chart and role map | D-01 | Owen | P1 / General | Ready - verify names |
| 1.02 | Formation, good standing, ownership, beneficial owners, and KYC materials | D-01 | Owen | P1 / Named | Collect for all four entities |
| 1.03 | Board and signing authority | D-01 | Owen | P1 / General | Routine approvals share; strategy redacted |
| 2.01 | Blue Mesa site option and amendments | D-02 | Elena | P1 / General | Critical; expires Oct. 31 |
| 2.02 | Survey, easements and title materials | D-02 | Elena | P1 / General | Collect current title, survey, easement, and amendment set |
| 2.03 | Land-use, construction and life-safety permits | D-03 | Elena | P1 / General | Collect requested permits; current status is not evidenced |
| 3.01 | Utility service agreement and amendments | D-04,D-05 | Elena | P1 / General | Ready; consent review required |
| 3.02 | Tariff, invoices and energy-price schedules | D-04 | Marcus | Hold -> Clean | Disclosure conflict; GC/CFO decision |
| 3.03 | 24 MW delivery evidence and milestone reconciliation | D-05 | Elena | P1 / General | Gap: 12 MW Jan. 15 + 12 MW Apr. 1 |
| 3.04 | One-lines, load study, transformers and switchgear | D-06 | Rina | P1 / Named | Current one-line ready; load study draft |
| 4.01 | Design set, construction schedule and punch list | D-08 | Elena | P1 / Named | Collect current design set, construction schedule, and punch list |
| 4.02 | Facility commissioning and certificates | D-08 | Elena | P2 / General | In progress |
| 5.01 | B200 BOM and supplier purchase documents | D-09 | Rina | P1 redacted / P2 Clean | Unredacted clean-team release |
| 5.02 | Serial inventory, title and delivery schedule | D-09 | Rina | P1 / Named | Serials not final; title chain partial |
| 5.03 | Crestline credit, collateral, UCC and release | D-09,D-18 | Marcus | P1 / Clean | Priority; lender consent required |
| 5.04 | OEM warranties, RMA and spares | D-10 | Rina | P1 redacted / P2 Clean | Redacted Phase 1 release; unredacted clean-team release in Phase 2 |
| 6.01 | Network topology, port map and oversubscription | D-11 | Rina | P1 / Named | Topology ready; port map in review |
| 6.02 | NorthSpan agreement, order and test plan | D-11,D-24 | Rina | P1 / Named | Include despite value threshold; consent review |
| 7.01 | Cooling design basis and capacity model | D-07 | Rina | P1 / Named | Current design ready |
| 7.02 | Cooling commissioning refresh | D-07 | Elena | P1 gap / P2 | Kestrel refresh required for B200 build |
| 7.03 | PolarLoop O&M agreement and records | D-07,D-24 | Rina | P1 / General | Include despite value threshold; consent review |
| 8.01 | SOC 2 Type II and control exceptions | D-12 | Rina | P1 / Named | Current report ready |
| 8.02 | Physical security and access records | D-12 | Rina | P1 / Named | Review personal information |
| 8.03 | Encryption, logging, incident and data terms | D-12,D-22 | Rina | P1 / Named | Data map incomplete |
| 9.01 | Operating procedures, staffing, monitoring and maintenance | D-13,D-23 | Rina | P1 / General | Collect operating procedures, staffing, monitoring, and maintenance policy |
| 9.02 | Availability, outage and incident history | D-13,D-14 | Rina | P2 / Named | Campus pre-operational; affiliate history only |
| 9.03 | Proposed service levels, acceptance, and benchmark plan | D-13 | Rina | P1 / General | Collect proposed service levels and acceptance criteria |
| 10.01 | Buyer mandate, offer and price build | D-16 | Ava | P1 / Clean | Price model review required |
| 10.02 | Term sheet and capacity agreement | D-16 | Ava/Owen | P1 / General | Term sheet logged; collect offer, price build, and draft capacity agreement |
| 10.03 | Existing capacity commitments | D-15 | Ava | P1 / Clean | Certification required |
| 11.01 | Financial statements and project budget | D-17 | Marcus | P2 / Clean | Budget ready; statements in review |
| 11.02 | Funding plan, liquidity, and proposed parent-guarantee credit support | D-17,D-18 | Marcus | P2 / Clean | Collect proposed parent guarantee; update after lender consent |
| 12.01 | Insurance policies and claims | D-19 | Marcus | P1 / Named | Cyber and tech E&O unconfirmed |
| 13.01 | Claims, compliance and regulatory materials | D-20 | Owen | P2 / Named | Counsel review |
| 14.01 | Energy source, matching and emissions | D-21 | Elena | P2 / General | Hourly matching support missing |
| 14.02 | Water use and environmental reports | D-21 | Elena | P2 / General | Current reports ready |
| 15.01 | Consent and notice tracker | D-24 | Owen | P1 / Named | Five priority agreements; maintain weekly |

# 3. Gating issues and instructions

| Issue | Current evidence | Treatment | Owner / target |
| --- | --- | --- | --- |
| Power delivery | Buyer asks for 24 MW by Jan. 15. Utility material supports 12 MW Jan. 15 and 12 MW Apr. 1. | Do not characterize 24 MW at initial service as substantiated. Obtain utility clarification or a documented bridge plan. | Elena / immediate |
| Utility pricing | Buyer requests unredacted tariff and price support; operator instruction bars release pending approval. | Owen and Marcus decide clean-team protocol. Record any buyer objection; do not silently omit or release. | Owen / Aug. 14 |
| Site control | Site option is below the general material threshold and expires Oct. 31, 2026. | Include as critical evidence; confirm exercise, funding, consent, and long-form site control plan. | Elena / Aug. 14 |
| Cooling | Commissioning report predates the B200 expansion. | Kestrel refreshes thermal model and commissioning evidence; mark old report superseded for this purpose. | Elena/Rina / Aug. 20 |
| Hardware title | Northline holds purchase documents; Crestline has equipment collateral. | Collect title chain, UCC evidence, lender consent, and release mechanics before claiming unencumbered capacity. | Marcus/Owen / Aug. 17 |
| Supplier evidence | Buyer asks for unredacted provenance; operator instructs redacted Phase 1 release. | Release reviewed redacted copies in Phase 1 only if buyer accepts; unredacted copies go to clean team in Phase 2. | Rina/Owen / Aug. 17 |
| Entity scope | Buyer request names only Alder Ridge Compute LLC. | Include Holdings, Campus SPV, and Northline where rights or obligations sit; explain entity roles in the index. | Owen / Aug. 14 |
| Insurance | Property and casualty evidence exists; current cyber and technology E&O are unconfirmed. | Broker obtains policies, endorsements, limits, deductibles, and claims history; leave request open until verified. | Marcus / Aug. 17 |

External coordination points are Hart & Vale LLP / Nadia Hart for contracts, consents, privilege, and disclosure review; Granite Plains Electric Cooperative / Jordan Bell for utility evidence; NorthSpan Fiber / Priya Nair for carrier evidence; Crestline Infrastructure Credit / Samuel Frost for collateral and release mechanics; and Kestrel Infrastructure Advisory / Leah Kim for the cooling and commissioning refresh.

# 4. Consent tracker

| Agreement / provision | Trigger | Notice or consent / timing | Counterparty / owner | Status / next step |
| --- | --- | --- | --- | --- |
| Blue Mesa site option / assignment and change-of-control provisions | Assignment or change of control | Consent if triggered / before transaction or option exercise | Land owner / Owen and Elena | Open - review provision and seek consent if triggered |
| Utility service agreement / assignment, load-user, and disclosure provisions | Assignment, load-user change, or disclosure | Confirm notice, consent, and disclosure permission / before Phase 1 or transaction | Granite Plains / Owen and Elena | Open - confirm requirements and permitted disclosure |
| NorthSpan network agreement / assignment and third-party-use provisions | Assignment or customer use | Confirm notice or consent / before customer-access commitment | NorthSpan Fiber / Owen and Rina | Open - confirm transaction and customer-use rights |
| PolarLoop cooling O&M / assignment and control provisions | Assignment or change of control | Confirm notice or consent / before transaction | PolarLoop Services / Owen and Rina | Open - confirm consent and service continuity |
| Crestline equipment credit / lien, transfer, and customer-dedication provisions | Transfer or dedication of financed hardware | Lender consent and release mechanics / before capacity commitment | Crestline Infrastructure Credit / Owen and Marcus | Open - obtain consent and documented release mechanics |

# 5. Release cadence and controls

August 13: Freeze initial index, entity scope, owners, request mappings, access labels, and issue log.

August 17 - Phase 1: Release reviewed core evidence and approved redacted copies; publish an explicit gap list.

August 18: Review buyer comments, rejected redactions, and overdue gating evidence.

August 24 - Phase 2: Release second-wave evidence and unredacted material under agreed clean-team controls.

Ongoing: Issue dated delta indexes; archive superseded files; never replace a released file without a version record.

Record each upload's date, version or execution status, entity, DDRL mapping, owner, sensitivity, review status, and every redaction and basis. Keep missing, stale, or partial evidence open with an owner and next action. A plan entry never proves that a document exists.