# Capacity Agreement Deviation Report

Northstar Models review of provider draft

| Opportunity | CB-2026-041 |
| --- | --- |
| Client perspective | Northstar Models, Inc. - buyer |
| Compared | August 20 term sheet; August 28 negotiation summary; September 2 draft agreement |
| Purpose | Signing decisions and drafting instructions |

Recommendation: Do not sign the current draft. Preserve the three agreed changes, but correct the commercial, technical, acceptance, security, capacity-control, and remedy deviations identified below.

# 1. Signing priorities

| Priority | Items | Required disposition |
| --- | --- | --- |
| Signing blockers | Power and site evidence; hardware title, liens, and consents; provider authority and parent support; security schedule; objective fabric, storage, and acceptance; deposit; substitution | Evidence delivered and agreement corrected before signature |
| Material drafting fixes | Escalation schedule; power pass-through; SLA credits; delay remedies; maintenance; force majeure; assignment/use; dispute forum | Conform draft or obtain explicit Northstar approval |
| Preserve as negotiated | Staged ramp; 99.3% availability threshold with agreed credits; expansion option | Keep package intact and label as agreed |

# 2. Deviation analysis

## ISSUE_001 - Price escalation schedule

| Field | Assessment |
| --- | --- |
| Term sheet / text | 2% annual escalation; Agreement Section 4.1 also says 2%. |
| Draft deviation | Schedule 2 uses 3%, producing $3.193 rather than $3.162 in the second contract year, a $0.031/GPU-hour difference before rounding. |
| Classification | Adverse to Northstar; unexplained; internal agreement inconsistency. |
| Response | Correct Schedule 2 to 2% and recalculate every derived rate. |

## ISSUE_002 - Staged delivery

| Field | Assessment |
| --- | --- |
| Term sheet | All 1,024 GPUs by January 15, 2027. |
| Draft deviation | 512 GPUs January 15 and 512 GPUs February 1. |
| Classification | Adverse to original buyer position but expressly agreed on August 28. |
| Response | Preserve the staged ramp; confirm billing begins only when each tranche passes acceptance. |

## ISSUE_003 - Availability threshold

| Field | Assessment |
| --- | --- |
| Term sheet | 99.5% monthly availability. |
| Draft deviation | 99.3% monthly availability. |
| Classification | Adverse but expressly negotiated as part of a service-credit package. |
| Response | Accept 99.3% only if the agreed 12% credit rate and 50% cap are restored. |

## ISSUE_004 - Service-credit economics

| Field | Assessment |
| --- | --- |
| Negotiated position | 12% of monthly committed charges per percentage point below 99.3%; 50% monthly cap. |
| Draft deviation | 8% per point and a 25% cap. |
| Classification | Adverse, unexplained, and contrary to the package supporting the 99.3% concession. |
| Response | Restore the 12% rate and 50% cap in Sections 8.2 and 8.3. |

## ISSUE_005 - Power pass-through

| Field | Assessment |
| --- | --- |
| Term sheet | Power included up to $0.075/kWh; verified excess at cost, with invoices, 30 days' notice, audit, and all-in cap. |
| Draft deviation | All electricity charges, riders, taxes, surcharges, and allocated power costs pass through monthly, with no threshold, at-cost language, support, notice, audit, or cap link. |
| Classification | Materially adverse and potentially inconsistent with Northstar's $3.35/GPU-hour all-in cap. |
| Response | Reinsert the threshold and all controls; state expressly that permitted pass-through cannot breach the all-in cap. |

## ISSUE_006 - Security deposit

| Field | Assessment |
| --- | --- |
| Term sheet | Three months, creditable to final invoices and otherwise refundable. |
| Draft deviation | Four months and non-refundable. |
| Classification | Adverse, unagreed, and a buyer checklist hard stop. |
| Response | Restore the three-month refundable and creditable structure. |

## ISSUE_007 - Delay credits

| Field | Assessment |
| --- | --- |
| Term sheet | $300,000 per full week, capped at $2.4 million; termination after eight weeks. |
| Draft deviation | $150,000 per week, $2.5 million cap, termination after ten weeks. The draft says ten weeks at $150,000 equals $2.5 million; it equals $1.5 million. |
| Classification | Adverse and unexplained. The nominal cap does not cure the halved weekly remedy. |
| Response | Restore $300,000/week, $2.4 million, eight weeks, and internally consistent arithmetic. |

## ISSUE_008 - Fabric obligation

| Field | Assessment |
| --- | --- |
| Term sheet | At least one 400 Gb/s endpoint per GPU, with topology and port map. |
| Draft deviation | Only commercially reasonable high-speed interconnect; Provider may alter topology. |
| Classification | Adverse and a technical signing blocker because the obligation is no longer measurable. |
| Response | Restore the 400 Gb/s per-GPU floor and tie topology and port-map evidence to acceptance. |

## ISSUE_009 - Storage performance

| Field | Assessment |
| --- | --- |
| Term sheet | 6 PiB usable shared storage with 1.2 TB/s sustained read and 800 GB/s sustained write. |
| Draft deviation | The same figures are only design targets 'up to' those levels under undefined representative conditions. |
| Classification | Adverse and unexplained because the draft turns measurable performance obligations into qualified aspirations. |
| Response | Restore firm sustained-throughput commitments and define the workload, measurement window, remedy, and acceptance test. |

## ISSUE_010 - GPU substitution

| Field | Assessment |
| --- | --- |
| Term sheet / negotiation | B200 or later with equal or better specifications, only with Northstar consent; August 28 expressly says no H200. |
| Draft deviation | B200, H200, or other NVIDIA device with similar memory, without consent. |
| Classification | Materially adverse, unagreed, and a buyer hard stop. |
| Response | Limit substitution to B200 or later equal-or-better hardware with prior written consent. |

## ISSUE_011 - Acceptance

| Field | Assessment |
| --- | --- |
| Negotiated position | 72-hour burn-in, serial and inventory attestation, and NCCL at least 92% of the agreed reference. |
| Draft deviation | Provider-standard diagnostics and deemed acceptance after 24 hours; no inventory attestation or objective NCCL test. |
| Classification | Materially adverse and a signing blocker. |
| Response | Insert all three tests, the 92% threshold, cure and retest, and no deemed acceptance before testing completes. |

## ISSUE_012 - Planned maintenance

| Field | Assessment |
| --- | --- |
| Term sheet | No more than eight hours of planned maintenance per month with at least seven days' notice. |
| Draft deviation | Up to twelve hours per month with only five days' notice. |
| Classification | Adverse and unexplained: the maintenance allowance increases by 50% and notice is shortened by two days. |
| Response | Restore the eight-hour monthly limit and seven-day notice period. |

## ISSUE_013 - Force majeure exit

| Field | Assessment |
| --- | --- |
| Term sheet | Termination after 90 consecutive days of material nonperformance. |
| Draft deviation | Termination only after 180 days. |
| Classification | Adverse and unexplained; doubles Northstar's exposure to unavailable capacity. |
| Response | Restore 90 days or add an earlier capacity-shortfall termination right. |

## ISSUE_014 - Assignment and customer use

| Field | Assessment |
| --- | --- |
| Term sheet | Affiliate assignment without consent and workload allocation to named controlled customers while Northstar remains liable. |
| Draft deviation | Provider consent for affiliate assignment and prohibition on all third-party use. |
| Classification | Adverse and inconsistent with agreed operating flexibility. |
| Response | Restore affiliate assignment and the named controlled-customer use right; retain the no-unrestricted-resale rule. |

## ISSUE_015 - Capacity control conditions

| Field | Assessment |
| --- | --- |
| Term sheet | Definitive documentation is conditioned on evidence of provider authority, utility delivery, facility commissioning, hardware title, liens, and required lender or third-party consents. |
| Draft deviation | Sections 12.1 and 12.2 give a qualified right-to-operate representation, permit financing liens, and leave necessary consents to Provider's own determination; the agreement contains no objective delivery condition for the required evidence. |
| Classification | Unresolved signing risk, not a drafting detail. The current language does not prove that the contracting entity controls the capacity it promises. |
| Response | Make the evidence and required consents conditions to signing or service commencement, identify permitted liens, and require objective title and release evidence. |

## ISSUE_016 - Parent support

| Field | Assessment |
| --- | --- |
| Term sheet | An enforceable guarantee from Alder Ridge Compute Holdings, Inc. is a condition to the definitive agreement. |
| Draft deviation | Section 12.3 postpones even the form and amount of parent support until after signing. |
| Classification | Materially adverse and a signing blocker because agreed credit support is absent. |
| Response | Attach and execute the agreed parent guarantee at signing; do not defer its scope. |

## ISSUE_017 - Security schedule

| Field | Assessment |
| --- | --- |
| Term sheet | Current SOC 2 Type II and an agreed security schedule are conditions to the definitive agreement. |
| Draft deviation | Sections 9.1 and 9.3 rely on commercially reasonable safeguards and a security schedule that is not included in the draft package. |
| Classification | Unresolved hard stop because key controls, customer-managed keys, and audit-log obligations are not complete contractual commitments. |
| Response | Complete, review, and attach the security schedule before signing; preserve the current SOC 2, US data, customer-key, and exportable-log requirements. |

## ISSUE_018 - Dispute forum

| Field | Assessment |
| --- | --- |
| Term sheet | Confidential AAA arbitration seated in New York after executive escalation. |
| Draft deviation | Exclusive state or federal litigation in Virginia. |
| Classification | Adverse or approval-required due to confidentiality, discovery, appeal, and provider home-forum effects. |
| Response | Restore confidential arbitration unless Northstar expressly approves litigation. |

## ISSUE_019 - Expansion option

| Field | Assessment |
| --- | --- |
| Term sheet | No fixed expansion price. |
| Draft deviation | Option for a further 1,024 B200 GPUs at no more than $3.30/GPU-hour, exercisable by March 31, 2027. |
| Classification | Favorable to Northstar and expressly agreed on August 28. |
| Response | Preserve the option and confirm it is not weakened elsewhere. |

# 3. Execution checklist

| Condition | Current result | Action |
| --- | --- | --- |
| Provider authority and parent support | Not satisfied | Confirm Campus LLC authority and execute the agreed Holdings guarantee at signing. |
| 24 MW delivery evidence | Not satisfied | Reconcile 12 MW Jan. 15 plus 12 MW Apr. 1 against the contracted GPU ramp. |
| Site control | Open | Exercise or extend the October 31 site option and obtain required consent through the service term. |
| Hardware title, liens, and consents | Open | Complete title chain and serial allocation, Crestline consent, UCC review, permitted-lien definition, and release mechanics. |
| Objective network, storage, and acceptance | Not satisfied | Restore 400 Gb/s per GPU, firm storage throughput, 72-hour burn-in, serial attestation, and 92% NCCL threshold. |
| Security schedule | Not satisfied | Complete and attach the agreed schedule before signing; verify SOC 2, US data, customer-key, and log terms. |
| Commercial mandate limits | Not satisfied | Restore three-month refundable deposit and controlled power pass-through under the all-in cap. |
| Insurance and credit | Open | Confirm cyber and technology E&O coverage, financial capacity, and the final parent-support package. |
| Agreed negotiation package | Partially reflected | Keep staged ramp, 99.3% threshold plus original credits, and expansion option together. |