## Evidence Register
Blue Mesa AI Campus - Evidence Register | Blue Mesa AI Campus - Evidence Register | Blue Mesa AI Campus - Evidence Register | Blue Mesa AI Campus - Evidence Register | Blue Mesa AI Campus - Evidence Register | Blue Mesa AI Campus - Evidence Register | Blue Mesa AI Campus - Evidence Register | Blue Mesa AI Campus - Evidence Register | Blue Mesa AI Campus - Evidence Register | Blue Mesa AI Campus - Evidence Register | Blue Mesa AI Campus - Evidence Register | Blue Mesa AI Campus - Evidence Register
CB-2026-041 ¦ Working register ¦ August 12, 2026 ¦ Synthetic benchmark matter
ID | Category | Document or evidence | Entity | Owner | Date / version | Status class | Detailed status | Sensitivity | DDRL | Consent / materiality | Review note
E-001 | Corporate | Project entity and stakeholder map | Group | Owen Mercer | 2026-08-11 | Ready | Ready - verify names | General | D-01 | Covers four entities | Buyer request names only Alder Ridge Compute LLC; add SPV and operator.
E-002 | Corporate | Formation, good standing, ownership and beneficial owner pack | Holdings / Campus / Northline | Owen Mercer | Various | Partial | Partial | Named-party | D-01 | No | Northline beneficial-owner certification still missing.
E-003 | Site | Blue Mesa site option and amendments | Campus LLC | Elena Park | 2025-11-14 | Ready | Ready | General | D-02,D-24 | Assignment / change of control; below $500k | Operationally critical. Option exercise deadline is 2026-10-31.
E-004 | Power | Utility service agreement and amendment 1 | Campus LLC | Elena Park | 2026-06-18 | Ready | Ready - conflict | General | D-04,D-05,D-24 | Assignment / load-user change | Supports 12 MW on 2027-01-15 and another 12 MW on 2027-04-01; not 24 MW at initial service.
E-005 | Power | Utility tariff and energy-price schedules | Campus LLC | Marcus Hale | 2026 tariff | Hold | Hold - approval | Clean team | D-04 | Operator instruction conflicts with buyer request | Buyer requests unredacted support; GC and CFO approval required before release.
E-006 | Power | Utility invoices and deposit ledger | Campus LLC | Marcus Hale | 2026 YTD | Partial | Partial | Clean team | D-04 | No | Construction-service invoices only; production billing has not begun.
E-007 | Electrical | Current single-line diagram | Campus LLC | Rina Solberg | Rev 7 - 2026-08-05 | Ready | Ready | Named-party | D-06 | No | Current design document.
E-008 | Electrical | Load study and redundancy assessment | Campus LLC | Rina Solberg | Draft - 2026-08-09 | Partial | Partial | Named-party | D-06 | No | Engineer sign-off and final utility assumptions pending.
E-009 | Cooling | Kestrel cooling commissioning report | Campus LLC | Elena Park | 2026-05-30 | Stale | Stale - refresh | Named-party | D-07 | No | Predates July B200 expansion; not current proof for offered configuration.
E-010 | Cooling | B200 thermal design basis and capacity model | Campus LLC | Rina Solberg | Rev 2 - 2026-07-28 | Ready | Ready | Named-party | D-07 | No | Requires Kestrel commissioning refresh.
E-011 | Hardware | B200 purchase orders and supplier confirmations | Northline | Rina Solberg | 2026-07-19 | Ready | Ready - redact | Clean team | D-09 | Supplier confidentiality | Redacted Phase 1; unredacted Phase 2 clean team. Buyer may object.
E-012 | Hardware | Serial inventory and node allocation schedule | Northline | Rina Solberg | Draft - 2026-08-10 | Partial | Partial | Named-party | D-09 | No | Serials assigned for 640 GPUs; remainder pending supplier allocation.
E-013 | Financing | Crestline equipment credit agreement, UCC and collateral schedule | Northline | Marcus Hale | 2026-07-25 | Ready | Ready - consent | Clean team | D-09,D-18,D-24 | Lien / transfer / customer dedication | Priority lender consent and release mechanics required.
E-014 | Hardware | OEM warranty, integrator support and RMA process | Northline | Rina Solberg | 2026-07-19 | Ready | Ready - redact | Clean team | D-10 | Supplier confidentiality | Redacted Phase 1; unredacted Phase 2 clean team.
E-015 | Network | NorthSpan fiber services agreement and delivery order | Northline | Rina Solberg | 2026-07-02 | Ready | Ready - consent | Named-party | D-11,D-24 | Assignment / third-party use; $420k | Below threshold but operationally critical.
E-016 | Network | Fabric topology, port map and carrier test plan | Northline | Rina Solberg | Rev 3 - 2026-08-08 | Partial | Partial | Named-party | D-11 | No | Topology ready; final port allocation and test result pending.
E-017 | Cooling | PolarLoop cooling O&M agreement | Northline | Rina Solberg | 2026-04-12 | Ready | Ready - consent | General | D-07,D-24 | Assignment / control; $310k | Below threshold but operationally critical.
E-018 | Security | SOC 2 Type II report | Northline | Rina Solberg | Period ended 2026-06-30 | Ready | Ready | Named-party | D-12 | No | Review exceptions and bridge letter requirement.
E-019 | Security | Physical security and named-access procedure | Campus / Northline | Rina Solberg | Rev 4 - 2026-07-31 | Ready | Ready - privacy review | Named-party | D-12 | Personal information | Remove employee home contact details before release.
E-020 | Operations | Operations, staffing, maintenance and incident plan | Northline | Rina Solberg | Draft - 2026-08-06 | Partial | Partial | General | D-13,D-14,D-23 | No | Campus is pre-operational; affiliate incident history must be labeled as such.
E-021 | Commercial | Northstar offer, pricing model and preliminary term sheet | Alder Ridge Compute LLC | Ava Ruiz | 2026-08-08 | Ready | Ready - review | Clean team | D-16 | No | Reconcile power assumptions and all-in cap before release.
E-022 | Financial | Project budget, sources and uses, and group financials | Holdings / Campus | Marcus Hale | 2026 Q2 | Partial | Partial | Clean team | D-17,D-18 | No | Budget ready; reviewed group statements awaiting auditor release.
E-023 | Insurance | Property, casualty and business interruption policies | Campus / Northline | Marcus Hale | 2026 policy year | Ready | Ready | Named-party | D-19 | No | Current policies received.
E-024 | Insurance | Cyber and technology E&O policies | Northline | Marcus Hale | 2026 policy year | Missing | Missing | Named-party | D-19 | No | Coverage and limits unconfirmed; broker request open.
E-025 | Governance | Board approvals and transaction materials | Holdings / Campus | Owen Mercer | 2026 | Partial | Partial - review | Hold / General | D-01,D-16 | Privilege and strategy | Share routine approvals; redact bid strategy and valuation document by document.
E-026 | Sustainability | Energy source, renewable matching and water report | Campus LLC | Elena Park | 2026 | Partial | Partial | General | D-21 | No | Water report ready; hourly renewable matching support missing.

## Status Summary
Evidence Register Status | Evidence Register Status | Evidence Register Status | Evidence Register Status
Status class | Count | Meaning | Required handling
Ready | 14 | Reviewed evidence is available. | Confirm version and release label.
Partial | 9 | Only part of the requested evidence is available. | Keep request open with owner and next step.
Missing | 1 | No current evidence is in the register. | Collect or disclose the gap.
Hold | 1 | Evidence exists but may not be released yet. | Resolve approval, consent, privilege, or access.
Stale | 1 | Evidence no longer proves the current configuration. | Refresh before relying on it.